## Status Balance
SC26-10
Status of Projects Managed by the Convention Bureau
for the period 01 January to 31 August 2001
Project Number | Project Title / Description | Funding Income 2001 |  |  | Total Expenditures | Balance
|  | Carried forward from 31.12.00 |  |  | at 31.08.01
|  |  | CHF |  | CHF | CHF
7002-000 | Ramsar Advisory Missions (RAMs) | Carried forward | 101346.28 |  | 28617.6 | 72728.68
Technical missions, at the request of the countries concerned, to Ramsar sites included in the Montreux Record in order to prepare recommenda- tions on how to address the problems involved. Management Guidance Procedures (MGP) over the past triennium have been carried out in Costa Rica, Guatemala, Islamic Republic of Iran, Italy and Trinidad and Tobago. A joint government/Ramsar Commission was established in Greece.
Activities in 2001:
Two experts visited the Schinias wetlands in Greece.
A RAM was made to the Sumava Peatlands in the Czech Republic in June 2001
A RAM will be undertaken in the Llancanelo Site in Mendoza Argentina in November 2001.
The RC for Africa undertook a RAM to the Parc national de la Keran site in Togo in August 2001.
A future RAM to Chilika Lake, India for removal of this site from the Montreux Record has been requested.
Future RAMs planned for this year include the Mühlenberger Loch in Germany (24-26 September); the Ouse Washes in the UK (5-8 November); and the Srebarna site in Bulgaria (1-4 October tbc), a joint World Heritage/IUCN mission.
7026-000 | Twinning of Wetlands of International Importance
| (Camargue/Danube) | Carried forward | 6302.36 |  | 0 | 6302
A three-year project planned for the period 1993-1995 for assistance by the Bureau in designing and helping to co-ordinate information and expert exchanges between France and Romania for the management of the Camargue and the Danube Delta. Future activity in relation to the remaining funds will be determined in consultation with the Government of France.
7043-000 | Wetland Conservation in Poland | Carried forward | 6926 |  | 0 | 6926
Support for the development of a national wetlands plan and its implementation in Poland; also the publication in Polish and English of the resulting national wetland overview and action plan entitled The Strategy of Wetland Protection in Poland.
7056-000 | Neotropics: Training/Education (Wetlands for the Future) | Carried forward | 279304.92 | * | 164974 | 114331
Support for wetland training and education in the Neotropics in the context of the agreement between the Government of the United States and the Bureau concerning the partnership for effective implementation of the Convention in the Western Hemisphere in honour of the Convention's 25th Anniversary. Projects are jointly approved by the US Department of State, US Fish and Wildlife Service, and the Bureau. Expenditure to date has funded 121 projects in the Neotropics in the field of training and capacity building.
* The monies in the balance forward have
all been comitted for previous years'
projects.
Funding has also been provided to support four specialized workshops in Colombia, Mexico, the CARIBWA
Conference and the Turtle workshop in Belize. The project provided 8 specialists the chance to attend the
Millenium 2000 Wetland Event in Quebec City, Canada in August 2000.
7056-020 | There is a separate project specifically for coral reef activities. | Carried forward - Coral Reef | 28648.89 |  | 5004 | 23644.89
7056-030 | WFF 2001 | USA Dept of State - 2001 | 539730 |  | 64170 | 475560
This year 13 proposals were submitted and 8 projects and two workshops were approved.
7057-000 | Manual (French) | Carried forward | 12176.52 |  | 0 | 12176.52
Translation and publication of the French version of the Ramsar Manual. The remaining funds are to be used for updating the text and subsequently disseminating it.
7066-000 | 25th Anniversary Pledges | Carried forward | 62750.8 |  | 12103 | 50647.8
In honour of the Convention's 25th Anniversary, pledges from a number of Contracting Parties have been earmarked for support of goals listed in the Ramsar Strategic Plan 1997-2002. Certain Contracting Parties pledged funds to be used in their own countries. The amount carried forward represents part of the non-earmarked contribution from Switzerland (SFR 500,000). Five scientists were sponsored to attend the Asian Wetland Symposium in Penang, Malaysia in August 2001.
7070-000 | Special Requests Project | Carried forward | 0 |  | 17185 | 39273
The funds in this project are designed to be made available at short notice to governments, NGOs, and other bodies (normally within Ramsar Contracting Party States, though exceptionally in non-Party countries) for activities related to the Convention and Strategic Plan which only require limited funds. Expenditure to date has funded twelve projects.
|  | Transfer from defunct Unemployment provision | 31066
|  | Fideicomiso refund | 25391.63
A translation of the Ramsar Toolkit into Chinese was funded this year.
7071-000 | Swiss Grant 1997 | Carried forward | 8218.93 |  | 0 | 8218.93
The 1997 grant for work in Africa was used for the assessment of potential Ramsar sites in The Gambia; for initial studies on populations of water birds in a Ramsar site in Gabon; for the preparation of a management plan for a national park in Niger; for an emergency rehabilitation plan in a biosphere reserve in Senegal; for Wetlands International's 1997 African Waterfowl Census Report; and for seed funding for a project to evaluate wetland systems in the Southern African Development Community (SADC).
**The funds in the balance have all been committed.
7072-000 | MedWet 2 Co-ordination | Carried forward | 179994.96 |  | 264413.56 | -84418.6
WWF's Mediterranean Programme provided funds to cover the MedWet Co-ordinator's part-time salary and travel and office expenses in 1997 and 1998. For 1999 and 2000 the contributions came from the MAVA Foundation.
An advance has been made to the National Observatory, Athens which will be reimbursed.
7076-010 | Austrian-Kenyan Twinning Project on Studies on White
| Stork in their Wintering Grounds | Carried forward | 0 |  | 0 | 0
Support from the Austrian Federal Ministry for Environment for Ramsar to coordinate with the Ministry of Tourism and Wildlife of the Kenya Wildlife Service to start on Phase II of the project on the European White Stork in their wintering grounds. Sub-projects include a mini-poster on the distribution and ecology of the White Stork, a twinning programme between schools, communities & national park administrators and providing equipment for site managers.
|  | Austria pledged | 3280
7079-000 | Evian Project (1998-2000) | Carried forward | 71086 |  | 78308.9 | -7223.16
The Evian project, known formally as the 'Caring for Water Resources and Water Quality Initiative', is a portfolio of activities in support of the Convention, funded by the Groupe Danone (which includes the Evian mineral water company) and the French Global Environment Facility (FFEM), and developed with the support of the Government of France. the town of Evian, and in particular the Conservatoire du Littoral.
* Some activites in 1997 were subcontracted and funds were transferred to contractees.
7079- | Evian Project 2001 - 2002
010 to 080 | Danone has committed to continuing the Evian project and has promised funding of a total of FFR 2,000,000 over a period of two years. | Danone | 232271 |  | 84622.08 | 147648.92
During 2001 five projects were started, and during 2002 an additional three will be added.
2001's programme includes: A symposium on Mountain Living Waters; an Evian Encounter for Arab Countries, a Workshop through EACN China, various Communications projects and the Evian Exhibition.
7081-000 | Swiss Grant 1998 | Carried forward | 7482.01 |  | 0 | 7482.01
The 1998 grant for work in Africa covered the balance of seed funding for a project to evaluate wetland systems in the Southern African Development Community (SADC); development of an integrated management plan at a Ramsar site in Botswana; support for the development of a common approach to shared water catchment areas in Benin, Burkina Faso, Niger, and Togo; support for a public awareness campaign on invasive species in wetlands; completion of the national wetland policy in Zambia; and Wetland International's 1998 African Waterfowl Census Report.
7086-000 | Ramsar Promotional Book | Carried forward | 50000 |  | 9965.14 | 40034.86
This book will depict one significant Ramsar site for each Contracting Party.
| A consultant has been hired and a call for superior photographs has gone out to all parties. | Spain pledged | 85000
7087-000 | Japan Donations for Asian Region | Carried forward | 406040 |  | 100,000 | 306040
Voluntary contributions from Japan in the years 1997, 1998 and 1999 specifically for projects in the Asian region. Conditions for the use of this fund are being considered.
SFR 100,000 was approved for the Asian Regional Meetings in 2001 and 2002
7088-000 | Swiss Grant 1999 | Carried forward | 28206.69 |  | 6000 | 22206.69
Six projects were funded in Botswana, Burkina Faso, Cameroon and Nigeria.
A combined implementation of environment-related conventions in CAR,
Benin, Cameroon and Tanzania was established. A wetlands Inventory Training
program was initiated in Cameroon and Kenya.
7090-000 | Convention Outreach Programme | Carried forward | 83133.27 |  | 67260.98 | 15872.29
The 24th Standing Committee approved the use of the excess in the
Reserve fund be used to create the "Voluntary Fund for the Convention's
Outreach Programme". A consultant has prepared a
report on Implementing the Convention's Outreach Programme 1999-2002:
Reviewing and Action Plannning for Wetland Communication, Education
and Public Awareness. The report has been translated into French and Spanish.
7091-000 | GEF Iran | Carried forward | 16851.1 |  | 12872.63 | 34408.47
The Bureau acts as International Service Provider under contract to UNDP.
| Five expert consultants have been contracted to prepare studies on Wetland Appraisal, Legal and | UNDP | 30430
Institutional work, and Management and Training. All final reports have been submitted.
7093-000 | Swiss Grant 2000 | Carried forward | 36342.4 |  | 6600 | 29742.4
The Swiss Grant has provided funding for six projects which includes:
Botswana: Development of a management plan for the Okavango Delta.
Guinea: Implementing the Convention. Sierra Leone: Assistance to ratify
Ramsar sites. Madagascar: Management plan for Manambolomaty site.
As well, a public awareness & education programme has been started in
Ghana and Kenya, and a workshop was held in Mauritius.
7094-000 | STRP Working Groups | Carried forward | 106032 |  | 69220 | 48882
In 2000 the US Department of State generously contributed $40,000 to help the
| STRP implement the second Joint Work Plan with the Convention on Biological | UK - DoETR | 12,070
Diversity.
Consultants are preparing reports on the following subjects:
Development of Guidance on Climate Change & Wetlands; - Preparation of Guidelines for Water Allocations and
Management for COP8; and Wetlands, Water and Climate Change. A global review of Wetland Resources.
7095-010 | COP8 - Valencia, Spain 2002 - Administration | Spain, Ministry of Environment- Pledged | 721000 |  | 0 | 0
Expenditures relating to the Conference of the Parties to be held 18-26 November 2002.
The funding will cover the translationof documents before and during the COP; hiring of consultants and experts;
reproduction and distribution of documents; interpreters, per diems and travel for Bureau staff & COP proceedings.
7095-020 | COP8 - Sponsored Delegates | Spain - Pledged | 100000 |  | 0 | 0
Additional fundraising will be undertaken to achieve a total of CHF 900,000 to support delegates and observers
from developing countries and countries whose economies are undergoing transition to attend the Conference
of the Parties.
7095-030 | COP8 - Secondee | Spain - Pledged | 67333 |  | 3124 | -3124
Mr Carlos Villalba has been seconded from Spain as the Bureau's "COP8 Technical Support Officer" until
December 2002. Part of Mr Villalba's time will be devoted to working with the MedWet Coordination Unit in Athens.
7096-000 | European Regional Meeting - Bled Slovenia 13-18 October 2001 | Austria, Ministry of Agriculture, Nature Mgmt & Fisheries | 14899 |  | 25855 | 93142.57
|  | Hungary (US$ 10,000) | 17099
|  | Norway | 7000
|  | Sweden, SIDA | 20000
|  | Switzerland, BUWAL | 16000
|  | Switzerland, SDC | 20000
|  | UK, DEFRA | 24000
Pledged
|  | France, for translation | 34893
|  | Netherlands, Ministry of Agriculture, Nature Mgmt & Fisheries | 17222
|  | Denmark, DANCEE | 30600
|  | TOTAL | 201713
7097-020 | Asian Regional Meeting - Thailand, October 2001 | Sweden, SIDA | 34190 |  | 34066.18 | 123.82
7097-000 | Asian Regional Meeting - Middle East 2002 | Japan (from 7087) | 100,000 |  | 0 | 100000
7097-010 | Asian Regional Meeting - Iran, February 2002
7098-020 | African Regional Meeting - Zambia, November 2001 | Sweden, SIDA | 70000 |  | 50250 | 19750
7098-010 | African Regional Meeting - Algeria, 2002
7098-030 | African Regional Meeting - Benin, 2002 | MAVA Foundation | 50,000 |  | 0 | 50000
7098-040 | Summary Meeting African Region - Gland
7099-000 | South American Regional Meeting - Argentina, September 2001 | Argentina | 87022.5 |  | 69427 | 17595.5
7099-030 | Central/North American & Caribbean Regional Meeting - Honduras, September 2001 | USA, Dept of State | 89955
|  | Canada | 10000 |  | 77649 | 22306
7099-010 | Central/ North American & Caribbean Regional Meeting - Nassau, June 2002 | (In principle, the US has
pledged to support both
7099-020 | Americas Regional Meeting - Colombia, June 2002 | of the meetings in 2002.)
7100-000 | Swiss Grant 2001 | Switzerland | 140,000 |  | 148469 | 9531
| There are six initiatives which will be engaged this year: | OMPO | 18000
An integrated management plan for the Okavango Delta in Botswana; an invasive species initiative for all African
Contracting Parties; an African Waterfowl Census for all African CPs; Support for accession to the Convention
for Burundi, Mauritius and Sudan; Restoration of a new Ramsar site in Algeria; and Transboundary management
and Ramsar site designation in the Lake Malawi Basin for Malawi, Mozambique and Tanzania.
7101-000 | WWD 2002 | Spain - pledged | 32852 |  | 0 | 0
Production of materials (posters, stickers, etc.) for World Wetlands Day, 2 February 2002.
7500-000 | (SGF) | Carried forward:
| Small Grants Fund for Wetland Conservation and Wise Use | 7500-100 1995 | 20606 | * | 0 | 20606
| Assistance for wetland conservation and wise use initiatives in developing countries and countries whose economy is undergoing transition. The Fund's resources are being directed to small-scale projects not traditionally covered by larger funding agencies. Some of the funds in the project reflect 25th Anniversary Pledges. | 7500-200 1996 | 43170 | * | 0 | 43170
|  | 7500-300 1997 | 79670.48 | * | 17180 | 62490.48
|  | 7500-400 1998 | 101620 | * | 16000 | 85620
| * Funds from previous years are all committed for second payments to cotnracts. | 7500-500 1999 | 145343.46 | * | 19952.3 | 125391.16
| 1999 Income Received in 2001 | European H. C. Stamp Program | 15303 | +
|  | 7500-600 2000 | 121865.57 | +
| 2000 Income Received in 2001 | Sweden, SIDA for 2000 | 115921 |  | 104741 | 133046
|  | 7500-610 2000 Black Stork | 20000 | * | 16000 | 4000
|  | 7500-701 1999, Israel, Vermetid Reef | 8000 | * |  | 8000
7500 - 700 | Small Grants Fund 2001 | 2001 Income Received
Forty good quality proposals were submitted in response to the 2001 call for proposals. There were nine submitted from the African Region, 6 from the Americas, 8 from the Asian regional, 16 from the European region and one from Oceania. In total these projects amounted to CHF 1,325,121. These are presently awaiting review and recommendations from the STRP, and approval by the Standing Committee.
|  | Austria, Ministry of Agriculture, Nature Management & Fisheries | 12000 |  | 18787 | 213365
|  | UK, DEFRA | 49590
|  | USA, Dept of State, and Fish & Wildlife Service | 126275
|  | Belgium - 2001 Black Stork 7500-710 | 20000
2001 Pledged
|  | Germany, Ministry of Environment | 45264
|  | Japan, Ministry of Foreign Affairs | 100075
|  | TOTAL PROJECTED INCOME | 353204